## Sheet1
[18 empty] | PROJECT COSTS FOR CWIP & AM ENTRIES | [14 empty] | PROJECT COSTS FOR ACTUALS & ENTITYWIDE GENERAL LEDGER ENTRIES
[12 empty] | Total Project Costs |  |  | Capital Improvements (Bldngs/Bldng Improvements/Land Improvements) |  |  | Infrastructure |  |  | Equipment (Furnishings) |  |  |  | Expensed & Transfer-Out Costs |  | A&E Commitment of Operational Budget |  |  | State Building Energy Conservation Program (SBECP) |  |  |  | Agency Proprietary Funding / Split Funded Projects |  |  | RMTD Funding | SEFA
[5 empty] | PROJECT STATUS REPORT | [9 empty] | State Capitalization Threshold 100,000 |  |  | State Capitalization Threshold 1,000,000 |  |  | State Capitalization Threshold 10,000 | [5 empty] | (For Planning & Professional Services Only) | [6 empty] | (Projects Funded with Proprietary & Governmental Funds)
[5 empty] | FYE 26 REPORT (As Of 7/13/2026) | [6 empty] | Include capital improvements, infrastructure, equipment, and expensed costs. |  |  | During planning & construction phases, agency adds current FY to CWIP. |  |  | During planning & construction phases, agency adds current FY to CWIP. |  |  | During planning & construction phases, agency adds current FY to CWIP. |  | Expensed Costs in 62000 Level are Non-Capitalizable Projects Such as Facility Studies. |  |  |  | A&E records an EW entry to | No entry needed | Both A&E & Agency perform current FY SBECP entries in |  | Both DEQ & Agency perform current FY SBECP entries in |  | For projects with agency 06XXX expenditures, agency must determine whether a capital contribution is |  |  |  | A&E records a capital contribution to the | A&E includes federal project expenditures
[5 empty] | *FINAL REPORT WILL BE PUBLISHED ON 7/16/2026 | [6 empty] | Does not include warranty inspection fees that have not been billed. |  |  | After Final Acceptance, agency retires prior FY CWIP & adds total project cost to AM. |  |  | After Final Acceptance, agency retires prior FY CWIP & adds total project cost to AM. |  |  | After Final Acceptance, agency retires prior FY CWIP & adds total project cost to AM. |  |  | No CWIP or AM Entries |  |  | offset agency AM entries for operating expenses. | for PY operating expenses | in accordance with MOM's XXXX for urrent FY only. |  | in accordance with MOM's XXXX for urrent FY only. |  | needed between Governmental and Proprietary Funds. |  |  |  | general fund for current FY RMTD expenditures. | & transfers on their SEFA report.
[12 empty] | All Account Level Expenditures |  |  | 64000 Level Expenditures |  |  | 64000 Level Expenditures |  |  | 63000 Level Expenditures |  |  |  | 62000 & 68000 Level Expenditures |  | A&E Fund 02030 62102 Expenditures |  | A&E Fund 05145 Expenditures |  | DEQ Fund 05147 Expenditures |  | Agency Proprietary Expenditures (06XXX Funds, Excluding RMTD's 06532 Fund) |  |  |  | Fund 06532 Expenditures | Federal Expenditures & Transfers
Agency | Agency Campus | SABHRS ORG # and Project Name | SABHRS ORG # | Estimated Budget | Project Status | Estimated Construction Completion Date | Substantial Completion/ Asset In-Service Date | Final Acceptance | FY Asset Add | Misc Info for Agencies | Current FY Project Expenditures | Prior FY Project Expenditures (61070 Datamine + A&E Operating) | Total Project Cost (61070 Datamine + A&E Operating) | Current FY Capital Improvement Expenditures | Prior FY Capital Improvement Expenditures | Total CWIP or Asset Cost | Current FY Infrastructure Expenditures | Prior FY Capitalizable Infrastructure Expenditures | Total CWIP or Asset Cost Infrastructure Projects | Current FY Equipment Expenditures | Prior FY Equipment Expenditures | Total CWIP or Asset for Equipment | Current FY Expensed Costs | Prior FY Expensed Costs | Pending Warranty Expense Included in Asset Cost (Assets Added Prior to FY26) | Pending Warranty Expense Not Included in Asset Cost (Assets Added In FY26) | Current FY A&E 02030 Expenditures (Agency Includes in CWIP & Asset Cost) | Prior FY A&E 02030 Expenditures (Agency Includes in CWIP & Asset Cost) | Current FY Fund 05147 Expenditures | Prior FY Fund 05145 Expenditures | Current FY Fund 05147 Expenditures | Prior FY Fund 05147 Expenditures | Current FY Agency Proprietary Expenditrures | Prior FY Agency Proprietary Expenditrures | Current FY Governmental Fund Expenditures (Including 06532 Capital Contribution) | Prior FY Governmental Fund Expenditures (Including 06532 Capital Contribution) | Current FY RMTD Expenditures | Current FY Federal Expenditures & Transfers to Capital Project Funds
DPHHS | MSH | 2011110103 WASTE WATER TREATMENT SYSTEM | 2011110103 | 5587000 | Warranty End 12/20/24 |  | 2023-12-20 | 2023-12-20 | 2024 | DPHHS told to include warranty inspection in cost of asset in FY25 for a total cost of 5,587,219.08.Requesting update from PM on closure/final billing.of 502.75. Nothing for DPHHS to do for this project. | 3915 | 5582801.33 | 5586716.33 | 0 | 0 | 0 | 3915 | 5582801.33 | 5586716.33 | 0 | 0 | 0 | 0 | 0 | 502.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MSH | 2011110105 LAGOON CLEANOUT & RESTORATION | 2011110105 | 822000 | Warranty End 8/11/26 |  | 2025-07-25 | 2025-08-11 | 2026 | Retire CWIP & Add asset, remaining contract amount will be paid as operating expense and may be reduced to $0. | 509184.88 | 302701.5 | 811886.38 | 0 | 0 | 0 | 509184.88 | 302701.5 | 811886.38 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MSH | 2011110106 WASTEWATER TREATMENT UPGRADE | 2011110106 | 601000 | Planning/CWIP | [5 empty] | 88299.19 | 0 | 88299.19 | 0 | 0 | 0 | 88299.19 | 0 | 88299.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | SWVH | 2011270101 SWVH ENCLOSED BLD WALKWAYS | 2011270101 | 8975000 | Warranty End 3/31/26 |  | 2024-12-10 | 2024-04-01 | 2026 | Retire CWIP & Add asset, 4900 of remaining CTA contract will be paid as operating. A&E is hoping to have a response from A&E firm on contract balance of 10,433.22 by 7/15/26.Please include 10,433.22 in project cost and A&E will do a NB entry so 64XXX accounts are zeroed out between agencies & Fiscal years. | 5522.56 | 7768311.83 | 7773834.39 | 5522.56 | 7768311.83 | 7773834.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | SWVH | 2011270102 SWVH 6TH COTTAGE | 2011270102 | 2200000 | Not Started | CO In process to extend |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20183007 FCA PROGRAM DEVELOPMENT | 20183007 | 2680000 | Not a Capital Project | NA | NA | NA | NA |  | 416526.29 | 396294.39 | 812820.68 | 1.2 | 25729.67 | 25730.87 | 0 | 0 | 0 | 0 | 0 | 0 | 416525.09 | 370564.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20191203 FOOD FACTORY EXPANSION | 20191203 | 32000000 | Warranty End 2/6/24 |  | 2022-10-24 | 2023-02-06 | 2024 | Requesting PM to final bill for $1500.00 warranty inspection. Waiting for Paradigm to respond on whether they will bill for warranty inspection. This won't change DOC's reported asset cost. | 0 | 3150887.41 | 3150887.41 | 0 | 3150887.41 | 3150887.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146329.91 | 0 | 4557.5 | 0 | 0
DOC | MSP | 2019120303 MCE FOOD FACTORY EMERG GEN | 2019120303 | 100000 | Warranty End 4/20/27 | 2026-02-19 | 2026-03-05 | 2026-04-20 | 2026 | Retire CWIP & Add asset. Do not include warranty inspection cost of $1500 for A&E will record expense in 62000 level. | 78587.36 | 24964 | 103551.36 | 78587.36 | 24964 | 103551.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 78587.36 | 24964 | 0 | 0 | 0 | 0
DMA | BSB AFRC | 20193303 BSB COUNTY ARMORY | 20193303 | 35258000 | Warranty End 1/23/26 |  | 2024-09-27 | 2025-01-23 | 2025 | If asset was added in FY25, asset cost needs to be updated for unforeseen costs in FY26 (FY25 project status asset cost was 35,258,481.69) | 45196.8 | 35250066.69 | 35295263.49 | 45196.8 | 35250066.69 | 35295263.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -187595.86
FWP | Lewistown Office | 20193503 CONSTRUCT LEWISTOWN AREA OFFC | 20193503 | 5500000 | Planning/CWIP | [5 empty] | 303383.25 | 483289 | 786672.25 | 303383.25 | 483289 | 786672.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | Glasgow HQ | 20193504 GLASGOW HQ ADDITION & MTG ROOM | 20193504 | 5083000 | Warranty End 6/2/26 | 2025-06-02 | 2025-06-02 | 2025-08-11 | 2026 | Retire CWIP & Add Asset. Includes A&E | 309176.92 | 4773428.61 | 5082605.53 | 309176.92 | 4773428.61 | 5082605.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | DOC Statewide | 2020100101 FCLTY-SPECIFIC PRGM & MSTR PLN | 2020100101 | 600000 | Planning/Study Only No CWIP |  |  |  |  | A&E will move to 62000 level | 0 | 66700 | 66700 | 0 | 66700 | 66700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MWP | 2020100102 WOMENS PRISON PLANNING | 2020100102 | 230000 | Planning/CWIP | [5 empty] | 225989 | 0 | 225989 | 225989 | 0 | 225989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20201203 MSP WATER SUPPLY/DISTRIBUTION | 20201203 | 2520000 | CWIP | 2025-05-30 |  |  |  | Waiting on retainage payout and FA | 33654.47 | 2435679.38 | 2469333.85 | 0 | 0 | 0 | 33654.47 | 2435679.38 | 2469333.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2020120301 UNIT F WATER SUPPLY UPGRADE | 2020120301 | 600000 | Planning/CWIP | [5 empty] | 3163 | 0 | 3163 | 0 | 0 | 0 | 3163 | 0 | 3163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20203001 CAPITOL BUILDING IMPROVEMENTS | 20203001 | 2323000 | Planning Only for Sup Projects | NA | NA | NA | NA | Agency should include planning costs with sub-projects | 94105.87 | 1322653.17 | 1416759.04 | 94105.87 | 1322653.17 | 1416759.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2020300101 LEGISLATIVE WORKSPACE RENO | 2020300101 | 956000 | Warranty End 10/10/23 for carpet |  | 2022-10-06 | 2022-10-10 | 2026 | Appears from recap some costs are furnishing & shouldn't be capitalized as improvements. Will have updated on 7/16/26 report. | 2250 | 577473.25 | 579723.25 | 2250 | 577473.25 | 579723.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23254.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2020300102 LEGISLATIVE CHAMBERS CARPETING | 2020300102 | 2621000 | [6 empty] | 11714.66 | 2587128.11 | 2598842.77 | 11714.66 | 2587128.11 | 2598842.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2020300103 CAPITOL BLDG IMPRVMNTS | 2020300103 | 26316000 | CWIP | 2027-11-02 |  |  |  |  | 1604507.98 | 639276.7 | 2243784.68 | 1604507.98 | 639276.7 | 2243784.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20203003 5 LCG BOILER UPGRADE | 20203003 | 629000 | Warranty End 10/2/24 |  | 2023-08-23 | 2023-10-02 | 2026 | Retire CWIP & Add Asset. | 5167 | 397395 | 402562 | 5167 | 397395 | 402562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20203005 RENOVATE EXECUTIVE RESIDENCE | 20203005 | 2341000 | On Hold | [5 empty] | 0 | 248889.85 | 248889.85 | 0 | 248889.85 | 248889.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Big Timber ESB | 20203102 BIG TIMBER ESB | 20203102 | 1917000 | Warranty End 5/31/25 |  | 2024-05-18 | 2024-05-31 | 2024 | MDT told to include warranty inspection in cost of asset in FY25.Requesting update from PM on closure/final billing. | 0 | 1914836.35 | 1914836.35 | 0 | 1914836.35 | 1914836.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Yellowstone Airport | 20203104 WEST YELLOWSTONE AIRPORT TRMNL | 20203104 | 46258000 | Waiting on final billing/CO's | 2025-11-27 | 2025-06-17 |  |  | Possible FA in FY26 | 1583491.15 | 44223252.91 | 45806744.06 | 1583491.15 | 44223252.91 | 45806744.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2487182.88 | 1583491.15 | 41736070.03 | 0 | 1583491.15
Livestock | Vet Diag & Ag Lab | 2020470101 VET DIAGNOSTIC & AG LAB | 2020470101 | 58808000 | CWIP | 2026-05-26 |  |  |  | Project has not reached final acceptance as of 7/14/26. | 17213414.58 | 41150975.67 | 58364390.25 | 17213414.58 | 41150975.67 | 58364390.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2021300201 PRKNG GRG RPRS 5 LST CHNC GLCH | 2021300201 | 1808000 | CWIP | 2026-06-01 |  |  |  |  | 866133.32 | 4272 | 870405.32 | 866133.32 | 4272 | 870405.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | WP HQ | 20213101 WP HEADQUARTERS OFFICE REMODEL | 20213101 | 2111000 | Warranty End 11/12/26 |  | 2024-12-10 | 2025-11-12 | 2026 | Retire CWIP & Add asset. Do not include warranty inspection cost of $2000 for A&E will record expense in 62000 level. | 77555.66 | 2029870.21 | 2107425.87 | 77555.66 | 2029870.21 | 2107425.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | Missoula LED | 20221001 PHYCF DOOR CONTROL SYSTEMS | 20221001 | 380000 | Planning/CWIP | [5 empty] | 0 | 7948.5 | 7948.5 | 0 | 7948.5 | 7948.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP/X Bldg | 20221002 X BLD DOOR CONTROL SYSTEMS | 20221002 | 500000 | Planning/CWIP | [5 empty] | 55582 | 13457.5 | 69039.5 | 55582 | 13457.5 | 69039.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MSH | 20221102 MAIN BLD. ROOF REPLACEMENT | 20221102 | 2130000 | CWIP | 2026-08-31 |  |  |  |  | 785917 | 113200 | 899117 | 785917 | 113200 | 899117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20221201 UNIT F BOILER SYSTEM/CONTROLS | 20221201 | 430000 | Warranty End 10/15/24 |  | 2023-10-15 | 2023-10-15 | 2025 | Warranty costs billed in FY26, but did not change asset cost reported to MDT in FY25. | 1900 | 442391 | 444291 | 1900 | 442391 | 444291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2022120201 ISOLATION CELL UPGRADES | 2022120201 | 100000 | Need FA & Planning contract billed |  |  |  |  | Waiting for confirmation with PM that Con'eer won't bill for remaining contract | 0 | 81473 | 81473 | 0 | 81473 | 81473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20221203 REPLACE MCE LAUNDRY EQUIPMENT | 20221203 | 800000 | Warranty End 12/31/26 |  | 2025-12-31 | 2025-12-31 | 2026 | Retire CWIP & Add asset. Do not include warranty inspection cost of $1650 for A&E will record expense in 62000 level. | 735121.21 | 16835 | 751956.21 | 735121.21 | 16835 | 751956.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 735121.21 | 16835 | 0 | 0 | 0 | 0
DPHHS | CFVH | 20221801 COURTYARD IMPROVEMENTS | 20221801 | 592000 | Warranty End 1/31/26 |  | 2024-11-13 | 2025-01-31 | 2025 | Cost of project needs to be updated for Supervisory fee had not been assessed at time of award due to budget constraints. | 15312.61 | 517069 | 532381.61 | 15312.61 | 517069 | 532381.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | CFVH | 20221803 ROOF RESURFACE | 20221803 | 1743000 | Warranty End 12/13/26 |  | 2024-10-30 | 2024-12-13 | 2025 | Cost of project needs to be updated for Supervisory fee had not been assessed at time of award due to budget constraints. | 39936.36 | 1332156.92 | 1372093.28 | 39936.36 | 1332156.92 | 1372093.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | CFVH | 20221804 MECHANICAL SYSTEM IMPROVEMENTS | 20221804 | 1213000 | Warranty End 8/28/25 |  | 2024-08-28 | 2024-08-28 | 2025 | Cost of project needs to be updated for Supervisory fee had not been assessed at time of award due to budget constraints. | 31770.33 | 1056136.73 | 1087907.06 | 31770.33 | 1056136.73 | 1087907.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MMHNCC | 20221901 MMHNCC ROOF REPLACEMENT | 20221901 | 2050000 | Warranty end 7/10/27 |  | 2025-05-22 | 2025-07-10 | 2025 | Unexpected costs in FY26, asset cost needs to be updated. | 8416.75 | 1648199.35 | 1656616.1 | 8416.75 | 1648199.35 | 1656616.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MSDB | Great Falls | 20222001 CAMPUS FIRE SYSTEM UPGRADES | 20222001 | 1127000 | Warranty end 5/20/26 |  | 2025-05-20 | 2025-05-20 | 2024 | Warranty costs billed in FY26, but did not change asset cost reported to MSDB in FY25.Bitterrot project cost 165,930.00 & Mustang project cost 844,456.29 | 2307.18 | 1008079.11 | 1010386.29 | 2307.18 | 1008079.11 | 1010386.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2307.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MWP | 20222601 DOOR CONTROLS SYSTEMS | 20222601 | 790000 | CWIP | 2026-06-30 |  |  |  |  | 501086.97 | 157019.54 | 658106.51 | 501086.97 | 157019.54 | 658106.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MWP | 20222602 MWP LIGHTING UPGRADE | 20222602 | 474000 | Warranty End 12/6/25 |  | 2024-12-06 | 2024-12-06 | 2025 | Asset added in FY25 & no change in project cost during warranty period. | 1170 | 451680.75 | 452850.75 | 1170 | 451680.75 | 452850.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420686.75 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MWP | 20222603 MWP TEMPERATURE CONTROL UPGRD | 20222603 | 100000 | Need FA |  |  |  | 2025 | Asset added in FY25 & no change in project cost during warranty period. | 333 | 24800 | 25133 | 333 | 24800 | 25133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2022300101 CAPITOL COMPLEX MP UPDATE | 2022300101 | 359000 | CC Master Plan Only | NA | NA | NA | NA | A&E will move to 62000 level | 62603.4 | 247912.6 | 310516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62603.4 | 247912.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2022300102 MAZUREK BUILDING RENOVATIONS | 2022300102 | 8155000 | CWIP |  |  |  |  | Project is for only elevator portion. Additional phase in planning. | 94216.1 | 5452171.93 | 5546388.03 | 94216.1 | 5452171.93 | 5546388.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2022300103 OBH RENO LEGISLATIVE SERVICES | 2022300103 | 4399000 | Warranty End 12/4/25 |  | 2024-11-26 | 2024-12-04 | 2025 | If asset was added in FY25, asset cost needs to be updated for unforeseen costs in FY26 (FY25 project status asset cost was 4,367,223.40) | 34761.05 | 4364703.4 | 4399464.45 | 34761.05 | 4364703.4 | 4399464.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2022300104 METCALF BUILDING UPGRADES | 2022300104 | 28000000 | CWIP | 2026-12-26 |  |  |  |  | 15726038.91 | 3967904.7 | 19693943.61 | 15726038.91 | 2224800.54 | 17950839.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1743104.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2022300105 MAZUREK SC SECURITY UPGRADES | 2022300105 | 200000 | GSD Entrusted | GSD will have info | GSD |  |  | GSD project, we just reimburse them | 128005.51 | 0 | 128005.51 | 128005.51 | 0 | 128005.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 0
MDT | Havre Shop | 20223101 HAVRE WELDING SHOP | 20223101 | 1503000 | Warranty End 8/5/25 |  | 2024-07-19 | 2024-08-05 | 2025 | Cost of project needs to be updated for Supervisory fee had not been assessed at time of award due to budget constraints.Waiting for PM to verify remaining Simonson contract amounts. | 38946.75 | 1413171.22 | 1452117.97 | 38946.75 | 1413171.22 | 1452117.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Lincoln Airport | 20223102 LINCOLN AIRPORT SNOW RMVL ESB | 20223102 | 1981000 | Warranty End 10/7/26 | 2026-10-07 | 2025-09-02 | 2025-10-07 | 2026 | Retire CWIP & Add asset, FY25 $15,920.31 A accrual will be reverted. | 170955.98 | 852344.56 | 1023300.54 | 170955.98 | 852344.56 | 1023300.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179170.96
MDT | Philipsburg ESB | 20223103 PHILIPSBURG 5-BAY ESB | 20223103 | 1043000 | Warranty End 4/1/26 |  | 2024-03-13 | 2024-04-01 | 2025 | Warranty costs billed in FY26, but did not change asset cost reported to MDT in FY25. | 2165 | 1971018.31 | 1973183.31 | 2165 | 1971018.31 | 1973183.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | White Sulfer ESB | 20223105 WHITE SULFUR 8-BAY ESB | 20223105 | 30000000 | Warranty End 2/19/25 |  | 2024-01-19 | 2025-02-19 | 2024 | MDT told to include warranty inspection in cost of asset in FY25. Reverting testing contract balance. | 0 | 2940349.98 | 2940349.98 | 0 | 2940349.98 | 2940349.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3782.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Harlem ESB | 20223106 HARLEM 6-BAY ESB | 20223106 | 2272000 | Warranty End 1/21/27 |  | 2025-12-09 | 2026-01-21 | 2026 | Retire CWIP & Add asset, but first A&E needs to verify remaining contracted amounts of 10,580. Waiting for PM to verify remaining Nelson contract amount. | 1346426.54 | 915134.23 | 2261560.77 | 1346426.54 | 915134.23 | 2261560.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Billings Shop | 20223108 BILLINGS WELDING/PLOW SHOP | 20223108 | 1631000 | Warranty End 11/19/25 |  | 2024-10-31 | 2024-11-19 | 2025 | Cost of project needs to be updated for Supervisory fee had not been assessed at time of award due to budget constraints.PM needs to verify unbilled Simonsen Architects amountt | 81251.94 | 1503603.94 | 1584855.88 | 81251.94 | 1503603.94 | 1584855.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Libby AFRC | 20223317 LIBBY RC LOADING DOCK EXP | 20223317 | 153000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Billings AFRC | 20223318 BILLINGS AFRC GENERATOR REPLC | 20223318 | 781000 | Warranty End 4/28/25 |  | 2024-02-15 | 2024-03-28 | 2024 | Warranty costs billed in FY26, but did not change asset cost reported to DMA in FY24. | 350 | 655899.21 | 656249.21 | 350 | 655899.21 | 656249.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262.5
DMA | Kalispell AFRC | 20223320 KALISPELL AFRC ROOF REPLACEMNT | 20223320 | 1000000 | Warranty End 11/6/26 |  | 2023-09-21 | 2024-11-06 | 2025 | Requesting PM to final bill for $630.00 warranty inspection. This will not change FY25 reported asset cost of 704,379.98. | 0 | 703749.98 | 703749.98 | 0 | 703749.98 | 703749.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Billings AFRC | 20223321 HAVRE UNHEATED BUILDING | 20223321 | 549000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | BSB AFRC | 20223323 BILLINGS UNHEATED STORAGE BLDG | 20223323 | 400000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex/DOR | 20223401 LIQUOR WAREHOUSE EXPANSION | 20223401 | 18512000 | CWIP | 2026-11-10 |  |  |  |  | 2298360.55 | 16396103.33 | 18694463.88 | 2298360.55 | 16396103.33 | 18694463.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex/MLEA | 20223701 MLEA SCENARIO BUILDING | 20223701 | 6458000 | Warranty End 3/14/27 |  | 2025-03-14 | 2025-03-14 | 2026 | Retire CWIP & Add Asset | 69091.52 | 4685747.03 | 4754838.55 | 69091.52 | 4685747.03 | 4754838.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | Eastern Land Office | 20223801 EASTERN LAND OFFICE & SHOP | 20223801 | 5260000 | Warranty End 10/11/25 |  | 2024-05-20 | 2024-10-11 | 2025 | Warranty costs billed in FY26, but did not change asset cost reported to DNRC in FY25. | 1000 | 5090762.07 | 5091762.07 | 1000 | 5090762.07 | 5091762.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | NW Land Office | 20223802 SWAN LAKE OFFICE SIDING | 20223802 | 463000 | Warranty End 5/29/26 |  | 2025-05-29 | 2025-07-14 | 2026 | Retire CWIP & Add asset | 145570.2 | 310144.96 | 455715.16 | 145570.2 | 310144.96 | 455715.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20224001 STATE HEALTH LAB RENOVATION | 20224001 | 20500000 | CWIP | 2026-04-30 |  |  |  | Project has not reached final acceptance as of 7/14/26. | 4760620.05 | 15300293.11 | 20060913.16 | 4738452.57 | 15300293.11 | 20038745.68 | 0 | 0 | 0 | 22167.48 | 0 | 22167.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4255543.56
DOA | Capitol Complex | 2022400101 COGSWELL ST HEALTH ROOF RPLC | 2022400101 | 1500000 | Not Started | [5 empty] | 12000 | 0 | 12000 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | BSB Re-Entry | 2023100101 BSB RE-ENTRY SERVICES UPGRADES | 2023100101 | 4574000 | Warranty End 12/5/26 |  | 2025-08-15 | 2025-12-05 | 2026 | Retire CWIP & Add asset. Do not include warranty inspection cost of $3800 for A&E will record expense in 62000 level. Includes | 1648773.05 | 2921668.9 | 4570441.95 | 1648773.05 | 2921668.9 | 4570441.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 246200 | 0 | 0 | 0 | 0 | 0 | 0 | 1402573.05
DOC | Watch East | 20231002 WATCH EAST DEFERRED MAINT | 20231002 | 221000 | Warranty End 6/5/26 |  | 2025-06-05 | 2025-06-05 | 2025 | Final billing for $450.00 warranty inspection occurred in FY26. This will not change FY25 reported asset cost.of 217,800.13 | 450 | 217350.13 | 217800.13 | 450 | 217350.13 | 217800.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | Eastmont | 20231003 EASTMONT HVAC REPAIRS/RPLCMNTS | 20231003 | 200000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MSH | 20231101 MSH COMPLIANCE UPGRADES | 20231101 | 21653000 | Warranty End 12/9/26 |  | 2025-12-09 | 2025-12-09 | 2026 | Retire CWIP & Add asset. A&E Iis hoping to have a response from A&E firm on contract balance by 7/15/26. | 10711484.68 | 10414845.86 | 21126330.54 | 10711484.68 | 10414845.86 | 21126330.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7426379.44
DPHHS | MSH | 2023110101 MSH ANACONDA WTR SERVICE UPGRD | 2023110101 | 277000 | Warranty End 7/10/25 |  | 2024-07-10 | 2024-07-10 | 2025 | Unexpected costs in FY26, asset cost needs to be updated. | 71992.5 | 195103.25 | 267095.75 | 0 | 0 | 0 | 71992.5 | 195103.25 | 267095.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MSH | 2023110102 INSTALL CAMPUS WTR SUPPLY SYST | 2023110102 | 7733000 | Planning/CWIP | GCCM TBD |  |  |  |  | 1077456.63 | 37000 | 1114456.63 | 0 | 0 | 0 | 1077456.63 | 37000 | 1114456.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195536.41
DPHHS | MSH | 2023110103 MSH MECHANICAL SYSTM RPLCMNT | 2023110103 | 11200000 | Planning/CWIP | GCCM TBD |  |  |  |  | 1191043.1 | 0 | 1191043.1 | 1191043.1 | 0 | 1191043.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MSH | 20231102 TEAMSTER GARAGE FIRE REPAIR | 20231102 | 649000 | Warranty End 3/3/27 | 2026-02-20 | 2026-02-19 | 2026-03-03 | 2026 | Retire CWIP & Add asset | 685990.07 | 0 | 685990.07 | 685990.07 | 0 | 685990.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231202 RED LIGHT/EMRGNCY NOTIF SYSTM | 20231202 | 1000000 | Planning/CWIP | [5 empty] | 4565.85 | 3626.94 | 8192.79 | 4565.85 | 3626.94 | 8192.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231203 SITE INFRASTRUCTURE STUDY | 20231203 | 300000 | Study Only | NA | NA | NA | NA |  | 0 | 296999.75 | 296999.75 | 0 | 296999.75 | 296999.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2023120301 SITE INFRASTRUCTURE UPGRADES | 2023120301 | 30385000 | Planning/CWIP | GCCM TBD |  |  |  |  | 505331.43 | 0 | 505331.43 | 0 | 0 | 0 | 505331.43 | 0 | 505331.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2023120302 RPLC CAMPUS WTR DIST SYSTEM | 2023120302 | 12192000 | Planning/CWIP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2023120303 ELECTRICAL&DISTRIBUTION UPGRD | 2023120303 | 13732000 | Planning/CWIP | [5 empty] | 155705.87 | 0 | 155705.87 | 155705.87 | 0 | 155705.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2023120304 MSP WASTE WATER SYSTEM UPGRADE | 2023120304 | 15000000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231204 MCE INDUSTRIES REPAIR | 20231204 | 700000 | Planning/CWIP | GCCM TBD |  |  |  |  | 1063.64 | 844.91 | 1908.55 | 1063.64 | 844.91 | 1908.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231206 REPLACE LOW-SIDE HOUSING | 20231206 | 153550000 | CWIP | 2027-09-30 |  |  |  |  | 55482755.58 | 14556813.76 | 70039569.34 | 55482755.58 | 14556813.76 | 70039569.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2023120601 LOW-SIDE HOUSING EXPANSION | 2023120601 | 129000000 | Planning/CWIP | GCCM TBD |  |  |  |  | 2806885.1 | 0 | 2806885.1 | 2806885.1 | 0 | 2806885.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231207 UNIT D RENOVATION | 20231207 | 18841000 | Planning/CWIP | GCCM TBD |  |  |  |  | 392017.21 | 1516135.88 | 1908153.09 | 392017.21 | 1516135.88 | 1908153.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231208 WATER LINE REPLACEMENT | 20231208 | 2958000 | CWIP | 2026-08-31 |  |  |  |  | 557863.76 | 807664.95 | 1365528.71 | 0 | 0 | 0 | 557863.76 | 807664.95 | 1365528.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231209 STAFF SRVCS AD TO WALLACE BLDG | 20231209 | 12800000 | Planning/CWIP | GCCM TBD |  |  |  |  | 364694.32 | 1146766.83 | 1511461.15 | 364694.32 | 1146766.83 | 1511461.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231210 MSP REPLACE ROOFS | 20231210 | 5600000 | Warranty End 3/24/27 |  | 2024-12-05 | 2025-03-25 | 2026 |  | 22680.26 | 4708677.24 | 4731357.5 | 22680.26 | 4708677.24 | 4731357.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP/X Bldg | 20231211 XANTHOPOULOS BUILDING REPAIRS | 20231211 | 4400000 | CWIP | 2026-05-01 |  |  |  |  | 1461601.38 | 56900 | 1518501.38 | 1461601.38 | 56900 | 1518501.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP/X Bldg | 2023121101 X BUILDING FIRE ALARM UPGRADE | 2023121101 | 750000 | CWIP | 2026-06-26 |  |  |  |  | 705259.34 | 0 | 705259.34 | 705259.34 | 0 | 705259.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231212 NEW MULTI-PURPOSE PROG BLDG | 20231212 | 9000000 | Planning/CWIP | GCCM TBD |  |  |  |  | 661553.1 | 414506.7 | 1076059.8 | 661553.1 | 414506.7 | 1076059.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231213 WLLC ENTRY SCRTY ENHNCMNTS | 20231213 | 3000000 | Planning/CWIP | GCCM TBD |  |  |  |  | 30194.05 | 119757.33 | 149951.38 | 30194.05 | 119757.33 | 149951.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231214 PERIMETER FENCE ENHANCEMENT | 20231214 | 1800000 | CWIP | 1/17/2026 CO signed 2/11 |  |  |  |  | 1161423.73 | 220363.42 | 1381787.15 | 1161423.73 | 220363.42 | 1381787.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20231215 MCE MVBLDG VENTLTN PNT&SNDBLST | 20231215 | 590000 | Planning/CWIP | GCCM TBD |  |  |  | Proprietary funded project, DOC will need to do capital contribution entry if needed. | 945.46 | 751.03 | 1696.49 | 945.46 | 751.03 | 1696.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945.46 | 751.03 | 0 | 0 | 0 | 0
DOC | PHYCF | 20231501 PINE HILLS ROOF REPLACEMENT | 20231501 | 1000000 | Need FA |  | ? | ? | 2026 | Retire CWIP & add asset. A&E will record remaining unbilled HGFA contract items as operating costs. | 867554.88 | 128744.27 | 996299.15 | 867554.88 | 128744.27 | 996299.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | PHYCF | 20231502 PINEHILLS UNT F SWR LN RPLCMNT | 20231502 | 500000 | Warranty End 10/1/26 |  | 2025-10-01 | 2025-12-01 | 2026 | Retire CWIP & Add asset. A&E will record remaining unbilled Con'eer Engineering contract items as operating costs. | 120211.25 | 268261.63 | 388472.88 | 0 | 0 | 0 | 120211.25 | 268261.63 | 388472.88 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | PHYCF | 2023150201 UTILITY TUNNEL HEATING SYS RPR | 2023150201 | 1200000 | Planning/CWIP | [5 empty] | 8850 | 0 | 8850 | 0 | 0 | 0 | 8850 | 0 | 8850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MMHNCC | 20231901 MMHNCC KEY CARD ENTRY SYSTEM | 20231901 | 185000 | Planning/CWIP | [5 empty] | 0 | 9700 | 9700 | 0 | 9700 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MMHNCC | 20231902 MMHNCC HEATED STORAGE UNIT | 20231902 | 360000 | Warranty End 10/16/25 |  | 2025-07-28 | 2025-10-16 | 2026 | Retire CWIP & Add asset for $312,620, remaining contract amount for warranty inspection & record drawings and will pay as operating expense. | 80119 | 232501 | 312620 | 80119 | 232501 | 312620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MSDB | Great Falls | 20232001 BROADBAND UPG & CONF SOLUTIONS | 20232001 | 885000 | Warranty End 10/10/25 |  | 2024-09-23 | 2024-10-10 | 2025 | Warranty costs billed in FY26, but did not change asset cost reported to MSDB in FY25. | 1768 | 883232 | 885000 | 1768 | 883232 | 885000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1768
MSDB | Great Falls | 2023200101 CAMPUS SECURITY CAMERA INSTALL | 2023200101 | 1457000 | Need FA |  |  |  |  | Retire CWIP, Add Asset | 0 | 282086.24 | 282086.24 | 0 | 282086.24 | 282086.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MSDB | Great Falls | 20232002 CREATE BUS LP UPDATE PRKNG LOT | 20232002 | 1130000 | Warranty End 3/4/26 | 8/7/2026 for new contract | 2025-01-16 | 2025-03-04 | Delete 2025 asset? | Added contract to project, delete asset & add back into CWIP? | 139646.31 | 340648.61 | 480294.92 | 139646.31 | 340648.61 | 480294.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | EMVH | 20232501 EMVH LAUNDRY IMPROVEMENTS | 20232501 | 436000 | Warranty End 5/2/25 |  | 2024-05-02 | 2024-05-02 | 2024 | FY24 DPHHS asset cost did not included remaining 599.50 warranty expense. PM has requested final billing but no change in DPHHS asset for A&E will pay remaiining contract as operating. Nothing for DPHHS to do. | 0 | 434138.36 | 434138.36 | 0 | 434138.36 | 434138.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MWP | 20232601 MWP COOLING SYSTEM UPGRADE | 20232601 | 1250000 | Warranty End 4/7/26 |  | 2025-04-07 | 2025-04-07 | 2026 | Retire CWIP & add asset. A&E will record remaining unbilled Con'eer Engineering contract items as operating costs. | 1400 | 1238538.04 | 1239938.04 | 1400 | 1238538.04 | 1239938.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MWP | 20232602 MWP HEATING SYSTEM UPGRADE | 20232602 | 1000000 | Warranty End 4/7/26 |  | 2025-04-07 | 2025-04-07 | 2026 | Retire CWIP & add asset. A&E will record remaining unbilled Con'eer Engineering contract items as operating costs. | 1400 | 988911.32 | 990311.32 | 1400 | 988911.32 | 990311.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MWP | 20232603 MWP PERIMETER FENCE/DOG YARD | 20232603 | 1000000 | CWIP | Spring 2026/Winter Shut-down |  |  |  |  | 531659 | 89095.41 | 620754.41 | 531659 | 89095.41 | 620754.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MWP | 20232604 MWP ROOF REPLACEMENT | 20232604 | 5000000 | CWIP | 2026-04-02 |  |  |  | Project includes Industries, Tower, & Main Re-roofs | 1146794.93 | 1728643.98 | 2875438.91 | 1146794.93 | 1728643.98 | 2875438.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20233004 ORIGINAL GOVNR MANSION RPRS | 20233004 | 600000 | CWIP | 2026-05-01 |  |  |  | Project has not reached final acceptance as of 7/14/26. | 526832.14 | 47787.43 | 574619.57 | 526832.14 | 47787.43 | 574619.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20233007 ELVTR MODFCTNS COGSWELL BLDG | 20233007 | 769000 | On Hold/Planning/CWIP |  | GSD |  |  |  | 0 | 32447.5 | 32447.5 | 0 | 32447.5 | 32447.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20233009 RF & MECH DPHHS 111 N. SANDERS | 20233009 | 1309000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20233010 ROOF RPLCMNT FWP HEADQUARTERS | 20233010 | 290000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | GF Comb Facility | 20233101 COMBINATION FCLTY GREAT FALLS | 20233101 | 15271000 | Planning/CWIP | [5 empty] | 248091.44 | 812151.55 | 1060242.99 | 248091.44 | 812151.55 | 1060242.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Kalispell Comb Facility | 20233102 COMBINATION FACILITY KALISPELL | 20233102 | 11950000 | CWIP | 2027-04-30 |  |  |  |  | 2589276.98 | 785132.14 | 3374409.12 | 2589276.98 | 785132.14 | 3374409.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Missoula Comb Facility | 20233103 COMBINATION FACILITY MISSOULA | 20233103 | 10500000 | Planning/CWIP | [5 empty] | 64956.2 | 518717.88 | 583674.08 | 64956.2 | 518717.88 | 583674.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Clearwater | 20233105 CLEARWATR RV DUMP STATION RENO | 20233105 | 1600000 | Cancelled | NA | NA | NA | NA | Per Mark, contract is being cancelled. Revert CWIP & need to do an entry to move to NB 62000 account. | 68923.18 | 147001.96 | 215925.14 | 68923.18 | 147001.96 | 215925.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Billings LAASF | 20233301 BILLINGS LAASF | 20233301 | 53160000 | CWIP | 2026-10-23 |  |  |  |  | 22654676.95 | 25881698.96 | 48536375.91 | 22654676.95 | 25881698.96 | 48536375.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22654676.95
DMA | Glasgow LAASF | 2023330101 BLAASF PHASE 2 | 2023330101 | 23071000 | Planning/CWIP | GCCM TBD |  |  |  |  | 21089.43 | 0 | 21089.43 | 21089.43 | 0 | 21089.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Gallatin AFRC | 20233314 GALLATN READINESS CNTR RF RPLC | 20233314 | 1483000 | Warranty End 1/13/28 |  | 2025-08-06 | 2026-01-13 | 2026 | Retire CWIP & Add asset. Do not include warranty inspection cost of $950 for A&E will record expense in 62000 level. | 181175.5 | 686901.5 | 868077 | 181175.5 | 686901.5 | 868077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85310.75
DMA | Gallatin AFRC | 20233315 GLLTN RC&FMS HVAC&CNTRLS RPRS | 20233315 | 1283000 | CWIP | 2026-04-30 |  |  |  | Project has not reached final acceptance as of 7/14/26. | 1070381.41 | 96004 | 1166385.41 | 1070381.41 | 96004 | 1166385.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802786.06
DMA | Gallatin AFRC | 2023331501 GLLTN RC&FMS TMPRTR CNTRL UPGR | 2023331501 | 193000 | CWIP | 2026-04-30 |  |  |  | Project has not reached final acceptance as of 7/14/26. | 47091 | 10435 | 57526 | 47091 | 10435 | 57526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24878.18
DMA | Helena AFRC | 20233316 FTH HAFRC LGHTNG&CNTRL MODFCTN | 20233316 | 524000 | Warranty End 6/9/26 |  | 2025-05-27 | 2025-06-09 | 2025 | Warranty period will end before FYE26, to date no change in asset cost added in FY25. | 0 | 523920.65 | 523920.65 | 0 | 523920.65 | 523920.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Statewide | 20233317 STATEWIDE SMART DEF MAINT PROG | 20233317 | 41000 | Not Started |  |  |  |  | This project is the parent project to AFRC sub-projects & will likely never have expenditures. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Helena AFRC | 2023331701 HAFRC ISOLATION VALVE INSTALL | 2023331701 | 164000 | Warranty End 1/29/26 |  | 2025-12-03 | 2026-01-20 | 2026 | Retire CWIP & Add asset. | 98372.43 | 55853.83 | 154226.26 | 98372.43 | 55853.83 | 154226.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74012.26
DMA | Kallispell AFRC | 2023331703 KAFRC EXTERIOR AND PARKING | 2023331703 | 464000 | CWIP | 2026-05-29 |  |  |  | Project has not reached final acceptance as of 7/14/26. | 124298.71 | 8930 | 133228.71 | 124298.71 | 8930 | 133228.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78929.68
DMA | Billings AFRC | 2023331705 BAFRC PARKING SUSTAINMENT | 2023331705 | 65000 | Planning/CWIP | [5 empty] | 4124.19 | 13315.81 | 17440 | 4124.19 | 13315.81 | 17440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -922.77
DMA | Havre AFRC | 2023331707 HAVRE RC ANNEX EXTERIOR | 2023331707 | 303000 | Warranty End 2/26/27 | 2025-12-31 | 2026-01-08 | 2026-02-26 | 2026 |  | 247442.14 | 26509.86 | 273952 | 247442.14 | 26509.86 | 273952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123721.07
DMA | Great Falls AFRC | 2023331708 GREAT FALLS AFRC EXTERIOR | 2023331708 | 328000 | CWIP | 2026-05-29 |  |  |  | Project has not reached final acceptance as of 7/14/26. | 258255.04 | 16418.07 | 274673.11 | 258255.04 | 16418.07 | 274673.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214274.21
DMA | Malta AFRC | 2023331709 MAFRC EXTERIOR SUSTAINMENT | 2023331709 | 879000 | Planning/CWIP | [5 empty] | 46590.83 | 17440 | 64030.83 | 46590.83 | 17440 | 64030.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32287.45
DMA | Havre AFRC | 2023331711 HAVRE RC ROOF REPLACEMENT | 2023331711 | 256000 | Warranty End 2/10/27 | 2025-09-30 | 2025-10-29 | 2026-02-10 | 2026 | Retire CWIP & Add asset. | 196394.74 | 30219.26 | 226614 | 196394.74 | 30219.26 | 226614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98197.37
DMA | Billings AFRC | 20233318 BLNGS READINESS & INNVTN CMPS | 20233318 | 78840000 | Planning/CWIP | [5 empty] | 318764.52 | 9135862.28 | 9454626.8 | 318764.52 | 9135862.28 | 9454626.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Helena AFRC | 20233319 HLN RDNSS HVAC&TMP CNTRL UPGRD | 20233319 | 3341000 | Planning/CWIP | [5 empty] | 229103 | 19129 | 248232 | 229103 | 19129 | 248232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174347.38
DMA | Helena AFRC | 2023331901 HAFRC TEMPERATURE CONTROL UPGR | 2023331901 | 1200000 | Planning/CWIP | [5 empty] | 49307 | 14299 | 63606 | 49307 | 14299 | 63606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37325.4
DMA | Helena DES | 20233320 DES COORDINATION CNTR EXPNSN | 20233320 | 6581000 | Planning/CWIP | [5 empty] | 93645.9 | 98725.85 | 192371.75 | 93645.9 | 98725.85 | 192371.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Helena DES | 20233321 DES STATE DISASTER WAREHOUSE | 20233321 | 5704000 | CWIP | 2026-08-10 |  |  |  |  | 4290636.58 | 444224.52 | 4734861.1 | 4160129.06 | 444224.52 | 4604353.58 | 0 | 0 | 0 | 130507.52 | 0 | 130507.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | Beartooth WMA | 20233507 BEARTOOTH WMA FCLTY UPGRADE | 20233507 | 8000000 | Planning/CWIP | [5 empty] | 203318.4 | 216340 | 419658.4 | 203318.4 | 216340 | 419658.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | Statewide Housing | 20233508 AGENCY STAFF HOUSING | 20233508 | 7500000 | Planning/CWIP | [5 empty] | 29500 | 247287 | 276787 | 29500 | 247287 | 276787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | L&C Cavern St Park | 2023350801 L&C CAVERN STATE PARK CARDWELL | 2023350801 | 300000 | Planning/CWIP | [5 empty] | 272745.8 | 0 | 272745.8 | 272745.8 | 0 | 272745.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | Lake Elmo St Park | 2023350802 LAKE ELMO STATE PARK BILLINGS | 2023350802 | 200000 | Planning/CWIP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | Lone Pine St Park | 2023350803 LONE PINE STATE PARK KALISPELL | 2023350803 | 100000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | MC Train Depot | 20233509 MILES CITY TRAIN DEPOT RENO | 20233509 | 2000000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | Central Services | 20233510 CENTRAL SERVICES SITE UPGRADES | 20233510 | 10343000 | CWIP | 2026-10-31 |  |  |  |  | 4515775.14 | 693986.6 | 5209761.74 | 4515775.14 | 693986.6 | 5209761.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | Central Services | 2023351001 Cntrl Srvcs Site Upgrd Ph2 & 3 | 2023351001 | 30030000 | Planning/CWIP | [5 empty] | 336358.71 | 0 | 336358.71 | 336358.71 | 0 | 336358.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex/MLEA | 20233703 MLEA BOILER RPLCMNT ADMIN BLDG | 20233703 | 269265 | Warranty End 10/15/26 |  | 2025-10-16 | 2025-10-16 | 2026 | Retire CWIP & Add asset. Do not include warranty inspection cost of $3615 for A&E will record expense in 62000 level. | 671497.7 | 85631 | 757128.7 | 671497.7 | 85631 | 757128.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOJ | Boulder | 20233704 MHP RF RPLCMNTS BOULDER CAMPUS | 20233704 | 1800000 | CWIP | 2025-11-06 |  |  |  | Additional phase of project pending award will update estimated completion date after award. | 913663.41 | 715114.91 | 1628778.32 | 913663.41 | 715114.91 | 1628778.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOJ | Missoula Crime Lab | 20233705 MSSLA CRIME LB EXP FSBLTY STDY | 20233705 | 106000 | Feasability Study Only | NA | NA | NA | NA | FYE25 Agency told to record $75,000 in 64000 as operating expense. No FY26 expense to date, but contract moved to 62000 level. | 18450 | 75000 | 93450 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 18450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOJ | Boulder | 20233706 MHP BOULDER DORM RENOVATIONS | 20233706 | 250000 | Warranty End 10/6/26 | 2026-10-06 | 2025-09-22 | 2025-10-06 | 2026 | Retire CWIP & Add asset. | 213292 | 11270 | 224562 | 213292 | 11270 | 224562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | NW Land Office | 20233801 STILLWATER UNIT SHOP RPLCMNT | 20233801 | 1384000 | Warranty End 1/2/27 | 2025-12-12 | 2026-01-02 | 2025-03-04 | 2026 | Retire CWIP & Add asset. Do not include warranty inspection cost of $1600 for A&E will record expense in 62000 level. | 843874.57 | 577279.85 | 1421154.42 | 843874.57 | 577279.85 | 1421154.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | Seedling Nursery | 20233802 SEEDLING NURSERY IMPROVEMENTS | 20233802 | 2797000 | In Litigation/CWIP | TBD |  |  |  | Project is on hold due to contractor/state lawsuit | 3280.06 | 644239.03 | 647519.09 | 3280.06 | 644239.03 | 647519.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | SW Land Office | 20233803 CLEARWATER RPLCMNT BUNKHOUSE | 20233803 | 1189000 | CWIP | 2026-11-02 |  |  |  |  | 693702.94 | 225478.2 | 919181.14 | 693702.94 | 225478.2 | 919181.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | SW Land Office | 20233804 ANACONDA BUNKHOUSE | 20233804 | 1181000 | CWIP | 2026-10-24 |  |  |  |  | 812760.63 | 194643.05 | 1007403.68 | 812760.63 | 194643.05 | 1007403.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | NE Land Office | 20233805 NELO FIRE READY ROOM | 20233805 | 493000 | CWIP | 2025-10-31 |  |  |  | Waiting for final payment and FA | 402889.75 | 45527 | 448416.75 | 402889.75 | 45527 | 448416.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | Central Land Office | 20233806 CLO DISPATCH CENTER EXPANSION | 20233806 | 615000 | Warranty End 10/24/26 |  | 2025-08-28 | 2025-10-24 | 2026 | Retire CWIP & Add asset. Do not include warranty inspection cost of $800 for A&E will record expense in 62000 level. | 274166.77 | 311410.94 | 585577.71 | 274166.77 | 311410.94 | 585577.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | SW Land Office | 20233807 CAMPUS LIGHTING UPGRADE | 20233807 | 20000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DLI | Polson JS | 20234201 POLSON JS LIGHTING UPGRADE | 20234201 | 25000 | Not Started/Verifying w/ DEQ | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DLI | Great Falls JS | 20234203 JOB SRVC GREATFALLS BLDG RNVTN | 20234203 | 5768000 | CWIP | 2026-05-31 |  |  |  |  | 3895529.44 | 455313 | 4350842.44 | 3895529.44 | 455313 | 4350842.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2024300201 COGSWELL BUILDING RENOVATION | 2024300201 | 50000 | Planning/CWIP | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2024300202 MITCHELL BUILDING RENOVATION | 2024300202 | 7304000 | CWIP | 2030-01-23 |  |  |  |  | 7721488.19 | 841559.12 | 8563047.31 | 6603848.86 | 841559.12 | 7445407.98 | 0 | 0 | 0 | 0 | 0 | 0 | 1117639.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2024300203 MITCHELL 2ND FLR E. WING RENO | 2024300203 | 2600000 | Warranty End 12/30/25 |  | 2024-12-16 | 2024-12-30 | 2025 | If asset was added in FY25, asset cost needs to be updated for unforeseen costs in FY26 (FY25 project status asset cost was 2,123,518.53) | 27480.98 | 2119676.03 | 2147157.01 | 27480.98 | 1784294.89 | 1811775.87 | 0 | 0 | 0 | 0 | 335381.14 | 335381.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2024300204 SRS BLDG ANALYSIS 111 SANDERS | 2024300204 | 101000 | Planning/CWIP | [5 empty] | 0 | 95898 | 95898 | 0 | 95898 | 95898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2024300205 W. SULLIVAN BUILDING RENO | 2024300205 | 25853000 | CWIP | 2027-03-30 |  |  |  |  | 7159770.48 | 997954 | 8157724.48 | 6707922.51 | 997954 | 7705876.51 | 0 | 0 | 0 | 0 | 0 | 0 | 451847.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 2024300206 MITCHELL EXTERIOR STAIR RPRS | 2024300206 | 300000 | Warranty End 3/3/26 |  | 2025-03-03 | 2025-03-03 | 2026 | Retire CWIP & Add Asset | 368.73 | 197037.2 | 197405.93 | 368.73 | 197037.2 | 197405.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20243003 LAD RELOCATION | 20243003 | 12500000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685990.07 | 0
DOA | Capitol Complex | 2024300301 LAD 4TH FLR MITCHELL RENO | 2024300301 | 2500000 | Warranty End 5/6/26 |  | 2025-05-07 |  | 2026 | Retire CWIP & Add Asset, Do not include warranty inspection cost of $3615 for A&E will record expense in 62000 level. A&E will verify contractor balance of 16,085 w/ PM by 7/16/26 report. | 376055.59 | 2083827.56 | 2459883.15 | 351506.03 | 1726037.36 | 2077543.39 | 0 | 0 | 0 | 24549.56 | 357790.2 | 382339.76 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | NW Land Office | 20243801 NW LAND OFFICE LIGHTING UPGR | 20243801 | 20000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | NW Land Office | 20243802 STILLWATER UNIT ENERGY UPGRADE | 20243802 | 10000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20245001 LEG BRANCH LRP & CPTL IMPRVMNT | 20245001 | 547500 | Planning/CWIP | [5 empty] | 0 | 542260.53 | 542260.53 | 0 | 542260.53 | 542260.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20245002 RENOVATN OF LEGISLATIVE SPACES | 20245002 | 12668000 | CWIP | 2026-07-11 |  |  |  |  | 8947215.93 | 1271382.82 | 10218598.75 | 8905634.43 | 1271382.82 | 10177017.25 | 0 | 0 | 0 | 40693.7 | 0 | 40693.7 | 887.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MSH | 20251102 SPRATT BLDG FCLTY FENCES | 20251102 | 20660000 | Planning/CWIP | [5 empty] | 2327566.64 | 0 | 2327566.64 | 2327566.64 | 0 | 2327566.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251201 WORK DORM TOILET UPGRADES | 20251201 | 300000 | Planning/CWIP | [5 empty] | 71645.11 | 0 | 71645.11 | 71645.11 | 0 | 71645.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251202 REPLACE RHU AND SAU DOORS | 20251202 | 8900000 | CWIP | 2027-01-22 |  |  |  |  | 7121750.55 | 248927.88 | 7370678.43 | 7121750.55 | 248927.88 | 7370678.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251203 MSP MVM & GP GENERATORS | 20251203 | 380000 | Not Started/Combined | [5 empty] | 6640 | 0 | 6640 | 6640 | 0 | 6640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251204 MSP MCE ROOF REPLACEMENT | 20251204 | 1350000 | Planning/CWIP | [5 empty] | 1104.96 | 0 | 1104.96 | 1104.96 | 0 | 1104.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251206 MSP MCE RESTROOM REPAIRS | 20251206 | 380000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251207 MSP MECHANICAL SYSTM RPLCMNT | 20251207 | 850000 | Planning/CWIP | [5 empty] | 308206.12 | 0 | 308206.12 | 308206.12 | 0 | 308206.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2025120701 HIGH SIDE KITCHEN MECH UPGRD | 2025120701 | 1500000 | Planning/CWIP | [5 empty] | 77968.9 | 0 | 77968.9 | 77968.9 | 0 | 77968.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2025120702 RESTRICTED HOUSING MECH UPGRD | 2025120702 | 600000 | Planning/CWIP | [5 empty] | 772.25 | 0 | 772.25 | 772.25 | 0 | 772.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2025120703 SECURE ACCESS UNIT MECH UPGRD | 2025120703 | 600000 | Planning/CWIP | [5 empty] | 831.75 | 0 | 831.75 | 831.75 | 0 | 831.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 2025120704 LAUDRY HVAC AND MECH UPGRD | 2025120704 | 1200000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251208 EDUCATION PRG BLDG&PRISON RPR | 20251208 | 3700000 | Planning/CWIP | [5 empty] | 18793.67 | 0 | 18793.67 | 18793.67 | 0 | 18793.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251209 GERIATRIC CARE UNIT | 20251209 | 14000000 | Planning/CWIP | [5 empty] | 328170.12 | 0 | 328170.12 | 328170.12 | 0 | 328170.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251210 OTP THEATER STABILIZATION | 20251210 | 200000 | Planning/CWIP | [5 empty] | 1380 | 0 | 1380 | 1380 | 0 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | MSP | 20251211 CONLEY LAKE UPGRADES | 20251211 | 300000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | MMHNCC | 20251901 UNIT D REMODEL FOR LICENSURE | 20251901 | 700000 | Warranty End 4/30/27 | 2026-03-18 | 2026-04-06 | 2026-04-30 | 2026 | Retire CWIP & Add asset.No Warranty inspection in contract. We are moving a procard purchase for $5069.72 and I'm sending you the invoice and I added the amount to today's Datamine.I don't know if there will be more equipment purchases and no change to the building asset cost of 328,190.65. | 333260.37 | 0 | 333260.37 | 328190.65 | 0 | 328190.65 | 0 | 0 | 0 | 5069.72 | 0 | 5069.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MSDB | Great Falls | 20252001 SELECTED HVAC SYSTEM UPGRADES | 20252001 | 2000000 | Planning/CWIP | [5 empty] | 8400 | 0 | 8400 | 8400 | 0 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32200 | 0
MSDB | Great Falls | 20252002 VOCATIONAL BLDG RENO DEMO | 20252002 | 4000000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | EMVH | 20252501 WTR INFLTRN EXTERIOR ENVLP RPR | 20252501 | 1900000 | Not Started |  |  |  |  | . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253001 GSD BOILER PLANT GENERATOR | 20253001 | 150000 | GSD Entrusted | GSD will have info | GSD |  |  | GSD project, we just reimburse them | 87415.86 | 0 | 87415.86 | 87415.86 | 0 | 87415.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253002 GSD PRKNG LOT RPR AND IMPRVMNT | 20253002 | 70000 | GSD Entrusted | GSD will have info | GSD |  |  | GSD project, we just reimburse them | 10000 | 0 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253003 GSD RPLC COMMODITIES FURNACE | 20253003 | 55000 | GSD Entrusted | GSD will have info | GSD |  |  | GSD project, we just reimburse them | 54950 | 0 | 54950 | 54950 | 0 | 54950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253004 2800 AIRPORT RD ACM ABATEMENT | 20253004 | 45000 | GSD Entrusted | GSD will have info | GSD |  |  | GSD project, we just reimburse them | 20999.36 | 0 | 20999.36 | 20999.36 | 0 | 20999.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253005 GSD CAMPUS FIRE ESCAPE REPAIRS | 20253005 | 25000 | GSD Entrusted | GSD will have info | GSD |  |  | GSD project, we just reimburse them | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253006 GSD AVIATION FCLTY UPGRADES | 20253006 | 1270000 | Not Started | [5 empty] | 24660 | 0 | 24660 | 24660 | 0 | 24660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253007 GOV MANSION HTNG FIRE ALRM SYS | 20253007 | 300000 | Planning/CWIP | [5 empty] | 15129.5 | 0 | 15129.5 | 15129.5 | 0 | 15129.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253008 PRINT & MAIL BLDG ROOF RPLCMNT | 20253008 | 825000 | Planning/CWIP | [5 empty] | 10420 | 0 | 10420 | 10420 | 0 | 10420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253010 CPTL BLDG LIGHTING RESTORATION | 20253010 | 125000 | Planning/CWIP | [5 empty] | 16036 | 0 | 16036 | 16036 | 0 | 16036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253011 CPTL CMPLX RESTROOM RENO | 20253011 | 625000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253012 STATEWIDE FEASIBILITY STUDIES | 20253012 | 346000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253013 CPTL COMPLEX ROOF REPLACEMENTS | 20253013 | 2600000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253014 CPTL CMPLX ELEVATOR SYST UPGRD | 20253014 | 5475000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253015 1227 11TH AVENUE RENOVATION | 20253015 | 3600000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253016 1300 11TH AVENUE RENOVATION | 20253016 | 4150000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253017 5 SOUTH LCG BLDG RENO | 20253017 | 17300000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20253018 720 MADISON RESIDENCE | 20253018 | 31000 | Initial cost is condition assessment |  |  |  |  | No entry needed for DOA. | 22117 | 8400 | 30517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22117 | 8400 | 0 | 0 | 22117 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Three Forks ESB | 20253101 ESB THR FRKS WLF CRK LDG GRSS | 20253101 | 5300000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDT | Missoula ESB | 20253102 PURCHASE OF EQUIP RPR SHOP | 20253102 | 8500000 | Building Purchased | NA | 2025-07-15 | NA | 2026 |  | 8472457.82 | 0 | 8472457.82 | 8472457.82 | 0 | 8472457.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Statewide | 20253304 SMART DEFERRED MAINT PROGRAM | 20253304 | 5682000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Great Falls ANG | 20253305 MTANG NEW TRAINING DROP ZONE | 20253305 | 1800000 | Land Purchased | NA | 2025-12-18 | NA | 2026 | Substantial completion date is date land was purchased | 1000751.62 | 0 | 1000751.62 | 1000751.62 | 0 | 1000751.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DMA | Helena Vet Cem | 20253306 VET INTERMENT PROCESSING CNTR | 20253306 | 600000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FWP | Cooney St Park | 20253507 STRG BLDG COONEY PARK DM B FAS | 20253507 | 375000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOJ | Boulder | 20253701 MHP BOULDER IBC HTNG SYS UPGRD | 20253701 | 2350000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOJ | DOA/MLEA | 20253702 MLEA AC INSTALLATION | 20253702 | 300000 | Planning/CWIP | [5 empty] | 26925 | 0 | 26925 | 26925 | 0 | 26925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOJ | DOA/MLEA | 20253703 MLEA NEW INDOOR FIRING RANGE | 20253703 | 10000000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | SW Land Office | 20253801 MISSOULA FRSTRY TRST OFFC BLDG | 20253801 | 2000000 | Planning/CWIP | [5 empty] | 12546 | 0 | 12546 | 12546 | 0 | 12546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DNRC | Central Land Office & NW Land Office | 20253802 HLN LBY PLN BUNKHOUSE OFFC ADD | 20253802 | 15000000 | Not Started | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DLI | Kalispell JS | 20254201 KALISPELL JOB SERVICE RENOVATN | 20254201 | 325000 | Not Started | [5 empty] | 525 | 0 | 525 | 525 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
St Grain Lab | Capitol Complex | 20254401 STATE GRAIN LABS HTNG SYS UPGR | 20254401 | 150000 | Planning/CWIP | [5 empty] | 10484 | 0 | 10484 | 10484 | 0 | 10484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20254501 LEARNING CNTR INFRASTR UPGRD | 20254501 | 700000 | Planning/CWIP | [5 empty] | 10056 | 0 | 10056 | 10056 | 0 | 10056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOC | Riverside | 20261001 RIVERSIDE FACILITIES RENO | 20261001 | 12000000 | Planning/CWIP | [5 empty] | 644986.2 | 0 | 644986.2 | 644986.2 | 0 | 644986.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 20263002 2 CARSON RESIDENCE | 20263002 | 100000 | Planning/CWIP | [5 empty] | 14520 | 0 | 14520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14520 | 0 | 0 | 0 | 14520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex/MLEA | 20263701 MLEA CMPS INFRSTRCTR FEASBLTY | 20263701 | 90000 | Study Only | NA | NA | NA | NA |  | 99243.83 | 0 | 99243.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99243.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOJ | Date Recovery Center | 20263702 DATA RECOVERY CENTER PLANNING | 20263702 | 75000 | Not Started | [5 empty] | 53520 | 0 | 53520 | 53520 | 0 | 53520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOJ | Boulder | 20263703 MHP HDQ FIRE ALARM UPGRADE | 20263703 | 230000 | Not Started | [5 empty] | 34510 | 0 | 34510 | 34510 | 0 | 34510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DPHHS | Commerce | 20264001 BEHAVIORAL HEALTH CENTER | 20264001 | 28500000 | Transfer to Commerce | NA | NA | NA | NA | No AM entries for approp/cash transferred to commerce. | 28500000 | 0 | 28500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DOA | Capitol Complex | 251401 MONTANA HISTORY CENTER | 251401 | 107875000 | CWIP | 2026-06-01 |  |  |  |  | 13015348.78 | 94379644.69 | 107394993.47 | 13015348.78 | 94379644.69 | 107394993.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620060 | 247505.52 | 202798.95 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Totals | 267759996.27 | 419941100.52 | 687701096.79 | 233853251.76 | 407248735.66 | 641101987.42 | 2979922.11 | 9629212.04 | 12609134.15 | 222987.98 | 693171.34 | 916159.32 | 30703834.42 | 2369981.48 | 10840.57 | 23814.5 | 36637 | 31654.5 | 0 | 620060 | 493705.52 | 623485.7 | 814654.03 | 5676062.82 | 1583491.15 | 41740627.53 | 893190.07 | 39256953.2
[10 empty] | Total of Cap Improvements, Infrastructure, Equipment, & Expensed Columns | 267759996.27 | 419941100.52 | 687701096.79
[10 empty] | Difference | 0 | 0 | 0